## Scope Checklist
COMPLETE RENOVATION - PENDING ITEMS + COST TRACKER | [6 empty] | RACI | Responsible | Accountable | Consulted | Informed
Project: | Jupiter |  |  | Baseline start: | 2026-10-05
Updated: July 2, 2026 - costs per Project Status & Cost Summary PDF
Schedule proposal Sep 24, 2026 (session 2026-ACTA-JUPITER-01): dates in F-H are driven by 'Schedule Logic'. N1-N12 = activities added from the 21-Sep session.
# | Category | Area | Scope Item | Status | Start Day | End Day | Effort (Hours) | Progress (%) | Exec Order | Owner | Total Cost | Balance Due | Vendor / Sub | Notes
PRE-CONSTRUCTION
1 | Pre-Construction | General | Architecture & Engineering design and proposal | Pending | 2026-10-12 | 2026-10-30 | 60 | 0% | - |  |  |  |  | Plan Drafting, caculations, Architectural Plan, Electrical Plan, Plumbing Plan, Mechanical Plan,
2 | Pre-Construction | General | Determine specification sheets (Render) | Pending | 2026-10-05 | 2026-10-16 | 40 | 0% | [5 empty] | It defines the type of finish and material to be used
3 | Pre-Construction | General | Architecture & Engineering Approval | Pending | 2026-11-02 | 2026-11-06 | 6 | 0%
| Pre-Construction | General | Select provides and assign budget | Pending | 2026-10-19 | 2026-11-06 | 24 | 0% | [5 empty] | PO Created for each case, set the date for procurement Determine material supplier & Labor provider
4 | Pre-Construction | General | Property boundary survey | Complete |  |  |  | 100%
5 | Pre-Construction | General | HOA / ARB approval - Garage Door | Pending | 2026-10-19 | 2026-11-06 | 3 | 0% | -
6 | Pre-Construction | General | HOA / ARB approval - exterior paint | Pending | 2026-10-19 | 2026-11-06 | 3 | 0% | -
7 | Pre-Construction | General | HOA / ARB approval - driveway | Pending | 2026-10-19 | 2026-11-06 | 3 | 0% | -
8 | Pre-Construction | General | HOA / ARB approval - Landscaping | Pending | 2026-10-19 | 2026-11-06 | 3 | 0%
9 | Pre-Construction | General | Obtain access to Online Portal | Pending | 2026-10-05 | 2026-10-06 | 2 | 0% | [5 empty] | Portal depends on the city: Town of Jupiter
10 | Pre-Construction | General | Certificate of insurance per trade per jurisdiction | Pending | 2026-10-26 | 2026-11-06 | 6 | 0% | [5 empty] | To: County City HOA
11 | Pre-Construction | General | Workers compensation per trade | Pending | 2026-10-26 | 2026-11-06 | 4 | 0% | [5 empty] | Ongoing document
12 | Pre-Construction | General | DBPR license per trade | Pending | 2026-10-26 | 2026-11-06 | 3 | 0%
13 | Pre-Construction | General | Notice of Commencement (NOC) | Pending | 2026-11-13 | 2026-11-17 | 4 | 0% | W1-01 | A |  |  |  | Based on Martin County: Obtain the correct file Fill-out Notarize Record
14 | Pre-Construction | Permits | Permits package submittal | Pending | 2026-11-09 | 2026-11-12 | 12 | 0% | - | - |  |  |  | Permit Application per trade https://www.jupiter.fl.us/98/Permit-Package-Submittal
15 | Pre-Construction | Permits | GC master permit - Residential alterations and additions | Pending | 2026-11-13 | 2026-12-14 | 8 | 0% | [5 empty] | Residential-AlterationsAdditions
16 | Pre-Construction | Permits | Mechanical permit | Pending | 2026-11-20 | 2026-12-14 | 4 | 0% | W1-04 | A |  |  |  | Mechanical
17 | Pre-Construction | Permits | Electrical permit | Pending | 2026-11-20 | 2026-12-14 | 4 | 0% | W1-03 | A |  |  |  | Please submit/upload plans in PDF format
18 | Pre-Construction | Permits | Plumbing permit | Pending | 2026-11-20 | 2026-12-14 | 4 | 0% | W1-02 | A |  |  |  | Plumbing
19 | Pre-Construction | Permits | Fence permit | Pending | 2026-11-13 | 2026-11-30 | 3 | 0% | W1-05 | A + V |  |  |  | Fences
20 | Pre-Construction | Permits | Driveway permit | Pending | 2026-11-13 | 2026-11-30 | 3 | 0% | W1-06 | A + V |  |  |  | Concrete, Patios, Decks, Slabs, Pavers Dec21.docx
21 | Pre-Construction | Permits | Gazebo permit | Pending | 2026-11-13 | 2026-11-30 | 3 | 0% | [5 empty] | Gazebo-Dec1.docx
22 | Pre-Construction | Permits | Garage-door permit | Pending | 2026-11-13 | 2026-11-30 | 3 | 0% | [5 empty] | Garage-Door-Replacement
23 | Pre-Construction | General | Demolition & Waste Management | In Progress | 2026-10-05 | 2027-01-26 | 10 | 90% | Ongoing |  |  |  |  | Dumpster / waste disposal
24 | Pre-Construction | General | Utilities | In Progress | 2026-10-05 | Ongoing | 2 |  | - |  |  |  |  | All utilities on autopay, up to date
INTERIOR - DEMO/STRUCTURE
52 | Interior - Demo/Structure | General | Interior demolition | Complete |  |  |  | 100% | - |  |  |  |  | Wall partitions, flooring, baseborads, doors, trim, bathrooms and kitchen
54 | Interior - Demo/Structure | General | Drywall repair / install + skim coat. Initial phase complete | Complete |  |  |  | 100% | W1-08 | V
N1 | Interior - Demo/Structure | General | Site protection + inventory (windows, railings, outlets, switches, smoke detectors) | Pending | 2026-10-05 | 2026-10-06 | 12 | 0% | - | A + V |  |  |  | Added from 21-Sep session [16:10]-[17:08]: tape/plastic on windows + railings; inventory and cover outlets, switches, smoke detectors before any new trade enters (lesson: tile crew cement on windows/railings); seal AC returns/registers, air handler off or filtered during dusty work
N2 | Interior - Demo/Structure | Structure | Structural engineering review - removed interior walls / truss bearing | Pending | 2026-10-05 | 2026-10-14 | 8 | 0% | - | A / Sub |  |  |  | Added from 21-Sep session [14:41]-[15:36]: engineer verifies roof trusses bear on perimeter walls; signed + sealed letter feeds A&E plans and framing permit
56 | Interior - Demo/Structure | General | Popcorn ceiling removal - flat finish & skin coat | Pending | 2026-10-07 | 2026-10-16 | 64 | 0% | - | Sub |  |  |  | All applicable areas included garage. Asbestos test on texture BEFORE scraping (lab 2-3 days); scrape + first flat coat now, final skim after MEP rough-in (recessed light cuts)
53 | Interior - Demo/Structure | General | Framing repairs / new partitions | Pending | 2026-12-15 | 2026-12-21 | 60 | 0% | - | V |  |  |  | Master Bathroom walls, Master closet walls, kitchen island. Requires engineer letter (N2) + GC master permit issued
N3 | Interior - Demo/Structure | Structure | Slab trench patch after underground plumbing (baths/kitchen) + slab inspection | Pending | 2026-12-21 | 2026-12-23 | 16 | 0% | - | V |  |  |  | Added from 21-Sep session [52:36]-[53:16]: underground plumbing inspection (P-trap, slope) must PASS before slab is closed; then slab/structure + plumbing inspections run together
57 | Interior - Demo/Structure | General | Concrete slab repair + tile infill under AC unit | Pending | 2026-12-15 | 2026-12-16 | 12 | 0% | W1-09 | V |  |  |  | Slab below equipment requires repair; cost in HVAC maintenance line; small demo required; V: demo tile in closet, install new tile
N4 | Interior - Demo/Structure | Inspections | Framing + MEP rough-in inspections (pre-cover milestone) | Pending | 2026-12-31 | 2027-01-07 | 8 | 0% | - | A |  |  |  | Added from 21-Sep session [35:22]-[40:28]: schedule via MGO; inspector usually next day; sealed large-format plans on site for inspector comments. Gate for closing walls (drywall)
| Interior - Demo/Structure | General | Drywall repair / install & finish. 2nd phase | Pending | 2027-01-08 | 2027-01-14 | 80 | 0% | W2-19 | V |  |  |  | Corner bead finish + paint at windows/doors. Hang + tape new partitions only after framing/MEP rough-in inspections PASS (N4)
| Interior - Demo/Structure | General | Drywall repair / install & finish. Final phase | Pending | 2027-01-15 | 2027-01-21 | 60 | 0% | W1-08 | V |  |  |  | Final sand + popcorn-ceiling final skim; surfaces ready for primer
N5 | Interior - Demo/Structure | General | Surface prep - primer on walls + ceilings | Pending | 2027-01-22 | 2027-01-26 | 40 | 0% | - | H |  |  |  | Added from 21-Sep session [18:17]-[19:44]: first coat = primer (wall/ceiling specific) before wet trades; improves adhesion, fewer paint coats
| Interior - Demo/Structure | General | Attic insulation | Not Needed |  |  |  |  | -
INTERIOR - ELECTRICAL
59 | Interior - Electrical | Contract | Electrical contract - overall | In Progress | 2026-10-05 | 2027-03-02 | - |  | W2-02 | Sub | 14000 | 7000 |  | $7,000 paid / $7,000 balance; final inspection pending; remaining: light fixtures + fans, all outlets + switches, kitchen chandelier, exterior floodlight, kitchen LED lighting, bath exhaust fans, bathtub electrical connection, LED mirror install
N6 | Interior - Electrical | Whole house | Make-safe exposed wiring from demolition (cap, label, temp lighting) | Pending | 2026-10-05 | 2026-10-05 | 6 | 0% | - | Sub |  |  |  | Added from 21-Sep session [14:34]-[14:41]: loose conductors left where partitions were removed; cap/label live circuits before trades return
60 | Interior - Electrical | Whole house | Electrical panel change out | In Progress | 2026-12-15 | 2026-12-16 | 12 |  | W1-10 | A + V |  |  |  | Permit pending; Panel already installed; V: add labels to cover, identify amperage + service; A: schedule + pass inspection
N7 | Interior - Electrical | Whole house | Electrical rough-in - relocated boxes, new kitchen/bath circuits | Pending | 2026-12-22 | 2026-12-30 | 60 | 0% | - | Sub |  |  |  | Added from 21-Sep session [12:07]-[12:38]: open-concept kitchen + removed walls = relocate boxes/switch legs; dedicated circuits fridge, oven, DW, disposal, hood; bath fans, tub, LED niches. Inspected in N4
61 | Interior - Electrical | Whole house | Outlets, switches, GFCI/AFCI | Pending | 2027-02-25 | 2027-03-01 | 24 | 0% | W2-02 | Sub |  |  |  | All pending install, including switches; in electrical contract; Include dedicated outlets for refrigerator + oven; Purchase W1 (A purchase session)
62 | Interior - Electrical | Whole house | Recessed lighting (LED) | In Progress | 2027-02-25 | 2027-02-26 | 12 |  | W2-02 | Sub |  |  |  | All installed and working except one recessed light in patio area
63 | Interior - Electrical | Whole house | Ceiling fans | Pending | 2027-02-26 | 2027-03-01 | 12 | 0% | W2-02 | Sub |  |  |  | Purchased (patio, master, bed 2, bed 3, living); awaiting install; in electrical contract
64 | Interior - Electrical | Dining | Dining fixture (kitchen chandelier) | Pending | 2027-03-01 | 2027-03-01 | 3 | 0% | W2-02 | Sub |  |  |  | Fixture on hand; reposition electrical box pending; install in electrical contract
65 | Interior - Electrical | Bathrooms | LED mirrors - install | Pending | 2027-03-02 | 2027-03-02 | 4 | 0% | W3-04 | V |  |  |  | In electrical contract remaining work; Purchase in W1 session (A)
66 | Interior - Electrical | Whole house | Smoke / CO detectors - replace all | Pending | 2027-03-02 | 2027-03-02 | 4 | 0% | W1-14 | V > A |  |  |  | Count pending; purchase pending; V: count detectors; A: purchase after count; existing detectors covered during protection (N1) - replace with interconnected units at trim
67 | Interior - Electrical | Whole house | Doorbell / smart doorbell | Pending | 2027-03-02 | 2027-03-02 | 2 | 0% | W2-02 | Sub
INTERIOR - PLUMBING
68 | Interior - Plumbing | Whole house | Plumbing redirects (in lieu of full repipe) | Complete |  |  |  | 100% | - |  |  |  |  | Lines redirected for new shower valves, new toilet position, new kitchen faucet + dishwasher locations; new fridge water line overhead in blue PEX
N8 | Interior - Plumbing | Whole house | Underground DWV rough-in (baths/kitchen) incl. P-traps + underground inspection PASS | Pending | 2026-12-15 | 2026-12-18 | 32 | 0% | - | V |  |  |  | Added from 21-Sep session [50:25]-[52:36]: a straight pipe without U/P-trap caused sewer gas and a finished shower had to be demolished. Camera-scope existing drains; do NOT close slab until inspector passes
N9 | Interior - Plumbing | Whole house | Water supply rough-in / top-out (shower valves, toilets, kitchen, fridge line) + pressure test | Pending | 2026-12-28 | 2026-12-30 | 24 | 0% | - | V |  |  |  | Added from 21-Sep session [53:00]-[53:16]: plumbing inspector checks open penetrations + blocking for liner; inspected in N4
71 | Interior - Plumbing | Whole house | Plumbing inventory check - supply lines, drainage, P-traps | Pending | 2026-12-31 | 2027-01-04 | 6 | 0% | W2-03 | V |  |  |  | Confirm inventory for all: kitchen faucet, bathroom faucets, toilets; build list (P-traps etc.); purchase gaps
69 | Interior - Plumbing | Contract | Final plumbing completion labor | Pending | 2027-02-25 | 2027-03-01 | 24 | 0% | W2-03 | V |  | 1500 | Victor | ~3 days labor at Victor's daily rate; final inspection pending; trim-out after cabinets, tops + tile (PROVISIONAL anchor in Schedule Logic)
72 | Interior - Plumbing | Whole house | Angle stops and supply lines throughout | Pending | 2027-02-25 | 2027-02-26 | 8 | 0% | W2-03 | V
70 | Interior - Plumbing | Whole house | Water heater | Not Needed |  |  |  |  | - |  |  |  |  | Working condition - keep
INTERIOR - HVAC
73 | Interior - HVAC | Whole house | AC unit replacement | Not Needed |  |  |  |  | - |  |  |  |  | Keeping existing unit; permit + inspection to cure open violation
74 | Interior - HVAC | Contract | HVAC maintenance + concrete slab repair | Pending | 2026-12-15 | 2027-01-28 | - | 0% | W1-09 | A / Sub | 2100 | 2000 |  | $1,000-$2,100 range; final cost depends on slab repaired in-house vs fully replaced; permit + inspection required (quick turnaround); A: hire service company
N10 | Interior - HVAC | Whole house | Duct modifications - removed partitions, kitchen hood + bath exhaust ducting | Pending | 2026-12-22 | 2026-12-28 | 24 | 0% | - | Sub |  |  |  | Added from 21-Sep session [12:07]-[12:38] + [33:19]: walls removed for open concept may carry supply/return runs; hood + bath fan ducts (master coupling pending) go in before walls close. Mechanical rough inspected in N4
77 | Interior - HVAC | Whole house | Ductwork inspection / repair / clean | Pending | 2027-01-27 | 2027-01-28 | 16 | 0% | W1-09 | Sub |  |  |  | Clean AFTER drywall sanding + primer (dust); returns/registers sealed and filters changed during dusty work
75 | Interior - HVAC | Whole house | HVAC coil cleaning | Pending | 2027-01-27 | 2027-01-27 | 4 | 0% | W1-09 | Sub |  |  |  | Part of maintenance line
76 | Interior - HVAC | Whole house | HVAC coolant refill service | Pending | 2027-01-27 | 2027-01-27 | 3 | 0% | W1-09 | Sub |  |  |  | Part of maintenance line
78 | Interior - HVAC | Whole house | AC diffusers | Pending | 2027-02-25 | 2027-02-25 | 4 | 0% | W1-14 | A |  |  |  | Purchase + install pending; A: purchase diffusers
79 | Interior - HVAC | Whole house | Thermostat | Pending | 2027-02-25 | 2027-02-25 | 2 | 0% | W1-14 | V |  |  |  | Return/exchange thermostat; install pending; V: pack thermostat + return via UPS
KITCHEN
N11 | Kitchen | Cabinetry | Cabinet order - field-verify dimensions, PO + fabrication (3-4 wk) | Pending | 2026-12-22 | 2027-01-21 | 6 | 0% | - | A |  |  |  | Added from 21-Sep session [25:34]-[29:44]: ready-made / semi-custom cabinets, not fully custom; fabrication 3-4 wk (a half-size kitchen took 2 wk); only long-lead item [28:29]. Order after framing fixes dimensions + appliance specs (fridge 36 in width/depth, cooktop, hood); timed to land at primer end to defer cash [28:00]. Layout must first be approved by Jaime [13:21]
80 | Kitchen | Cabinetry | Kitchen cabinets + bathroom vanities (combined contract) | In Progress | 2027-01-27 | 2027-01-28 | 16 |  | W1-11 | A + V | 21750 | 4875 | Noel | $16,875 paid / $4,875 balance; install by cabinet manufacturer, 1-2 days max; quality verification meeting Mon Jul 6, 11:00 AM; A & V both present at Noel appointment Mon Jul 6, 11 AM
81 | Kitchen | Countertops | Stone countertops + backsplash (kitchen + baths) | Pending | 2027-01-29 | 2027-02-09 | 12 | 0% | W1-12 | A / M | 5925 | 4500 | Martin | $3,950-$5,925 range at $50-$75/sq ft installed + fabricated; kitchen ~35 sq ft counter + ~25 sq ft backsplash; bath 2 ~8 sq ft; master ~11 sq ft; fabrication ~5 business days, install 1-2 days; CABINETS MUST BE FULLY INSTALLED BEFORE FIELD MEASUREMENTS; call Martin for quote; decide if kitchen differs from vanity tops + thresholds; A: request Martin appointment for same Monday Jul 6; Martin meeting Sat Jul 4 - V attends; M provides quote; A selects stone, purchases + makes down payment; M installs ~5 days after quote, subject to stone purchase + delivery availability
82 | Kitchen | Kitchen | Kitchen sink - purchase | Pending | 2026-12-31 | 2027-01-07 | 3 | 0% | W1-13 | A
83 | Kitchen | Kitchen | Kitchen faucet | Pending | 2026-12-31 | 2027-01-07 | 2 | 0% | W1-13 | V > A |  |  |  | Purchase or verify purchase; V: verify faucet already purchased; if not, A purchases
84 | Kitchen | Kitchen | Appliance package - purchase, transport, install | Pending | 2026-12-31 | 2027-01-14 | 16 | 0% | W1-14 | A | 9100 | 9100 |  | Samsung oven + microwave combo $3,700; cooktop $650; dishwasher $500; exhaust hood $500; garbage disposal $250; wine cooler $450; refrigerator $1,800; washer + dryer set $1,250; source via Facebook Marketplace where possible; delivery coordination + install scheduling pending; A: ongoing marketplace search; V: provide refrigerator depth (width confirmed 36 in); V: transport + install W1-W2 as items are acquired
N12 | Kitchen | Kitchen | Appliance install + hook-ups (oven, cooktop, DW, disposal, hood, fridge line) | Pending | 2027-03-02 | 2027-03-03 | 12 | 0% | - | V |  |  |  | Added: cooktop + sink templates go to the stone fabricator before fabrication; hook-ups need plumbing + electrical trim (dedicated oven/fridge outlets)
86 | Kitchen | Kitchen | Under-cabinet lighting | Pending | 2027-02-25 | 2027-02-25 | 4 | 0% | W1-14 | A |  |  |  | Select transformer; select LED strip; puck light selection, count + purchase; kitchen LED in electrical contract; A: purchase LED lighting for cabinetry
85 | Kitchen | Kitchen | Kitchen island | Not Needed |  |  |  |  | -
BATH - MASTER
87 | Bath - Master | Vanity | Vanity cabinetry - confirm quality | Pending |  |  |  |  | W1-11 | A + V |  |  | Noel | In cabinet contract
88 | Bath - Master | Vanity | Sink selection - double sinks | Pending |  |  |  |  | W1-13 | A |  |  |  | A purchases sinks
89 | Bath - Master | Vanity | Vanity stone top - select (~11 sq ft) | Pending |  |  |  |  | W1-12 | A |  |  | Martin | In stone contract line
90 | Bath - Master | Vanity | Double faucets + double sinks - install | Pending |  |  |  |  | W3-02 |  |  |  |  | Verify vanity height pending
91 | Bath - Master | Toilet | Toilet install + new wax ring | Pending |  |  |  |  | W1-20 | V |  |  |  | New toilet position (drain relocated); New flange if necessary; verify supply line + drainage positioning; One row per bathroom (master + secondary)
92 | Bath - Master | Tub | Tub install | Pending |  |  |  |  | W2-17 |  |  |  |  | Bathtub electrical connection in electrical contract; Bathtub electrical connection ASAP in W1 - ready for inspection; set tub in W2 after inspections pass
93 | Bath - Master | Shower | LED niche | Pending |  |  |  |  | W2-02 | V |  |  |  | ASAP - confirm inventory or place supply order
94 | Bath - Master | Shower | Shower drains - select + purchase (BOTH baths) | Pending |  |  |  |  | W1-13 | A |  |  |  | Needed on hand before pan liner / tile sequence
95 | Bath - Master | Shower | Shower prep - confirm metal frame distance + shower door frame support (BOTH baths) | Pending |  |  |  |  | W1-17 | V |  |  |  | Pre-liner check; do labor if needed; supports glass door install later
96 | Bath - Master | Shower | Durock + waterproofing install | Pending |  |  |  |  | W1-18 | V |  |  |  | Shower sequence steps 3-4: Durock, then waterproofing - after pan liner inspection passes
97 | Bath - Master | Shower | Pan liner install + inspection pass | Pending |  |  |  |  | W1-18 | V |  |  |  | Shower sequence step 2 (after step 1 framing); CANNOT start before permit issuance + plumbing/framing/slab inspections scheduled/passed
98 | Bath - Master | Shower | Bathroom tile installation - labor (BOTH baths) | Pending |  |  |  |  | W2-01 | Sub |  | 3500 |  | Complete bathroom tile install, both bathrooms; ~10 days total; Starts ONLY after framing, Durock, waterproofing + passed inspections (W1-18 sequence)
99 | Bath - Master | Shower | Metal trim (edge profile) - verify availability | Pending |  |  |  |  | W1-14 | V |  |  |  | V: confirm metal trim color + count
100 | Bath - Master | Shower | Threshold + bench top | Pending |  |  |  |  | W3-01 | M |  |  | Martin | Coordinate stone with countertop selection
101 | Bath - Master | Shower | Glass shower enclosure - MASTER | Pending |  |  |  |  | W3-03 | G | 3000 | 3000 | Gino | $2,500-$3,000; fabrication ~4 days; install 1-2 days; measurements pending; Gino: quote + install MASTER
102 | Bath - Master | Finishes | Paint all walls | Pending |  |  |  |  | W2-13 | H
103 | Bath - Master | Finishes | Pocket door - verify function + paint | Pending |  |  |  |  | W2-14 | H
107
104 | Bath - Master | Finishes | Bath hardware (towel bars, TP holder, etc.) | Pending |  |  |  |  | W3-04 | A > V |  |  |  | Purchase W1 (A - Amazon / online / retail); install W3
107
105 | Bath - Master | Ventilation | Exhaust fan | Pending |  |  |  |  | W3-04 | V |  |  |  | Duct install - coupling pending; fan install in electrical contract
BATH - SECONDARY
106 | Bath - Secondary | Vanity | Vanity cabinetry - confirm quality | Pending |  |  |  |  | W1-11 | A + V |  |  | Noel | In cabinet contract
107 | Bath - Secondary | Vanity | Sink selection - single sink | Pending |  |  |  |  | W1-13 | A |  |  |  | A purchases sinks
108 | Bath - Secondary | Vanity | Vanity stone top - select (~8 sq ft) | Pending |  |  |  |  | W1-12 | A |  |  | Martin | In stone contract line
109 | Bath - Secondary | Vanity | Faucet + sink - install | Pending |  |  |  |  | W3-02 |  |  |  |  | Verify vanity height pending
110 | Bath - Secondary | Toilet | Toilet install + new wax ring | Pending |  |  |  |  | W1-20 | V |  |  |  | New flange if necessary; verify supply line + drainage positioning; One row per bathroom (master + secondary)
111 | Bath - Secondary | Shower | LED niche | Pending |  |  |  |  | W2-02 | V |  |  |  | ASAP - confirm inventory or place supply order
112 | Bath - Secondary | Shower | Durock + waterproofing install | Pending |  |  |  |  | W1-18 | V |  |  |  | Shower sequence steps 3-4: Durock, then waterproofing - after pan liner inspection passes
113 | Bath - Secondary | Shower | Pan liner install + inspection pass | Pending |  |  |  |  | W1-18 | V |  |  |  | Shower sequence step 2 (after step 1 framing); CANNOT start before permit issuance + plumbing/framing/slab inspections scheduled/passed
114 | Bath - Secondary | Shower | Shower tile install | Pending |  |  |  |  | W2-01 | Sub |  |  |  | Labor in master line (both baths, $3,500); Sub - after W1-18 sequence + inspections pass
115 | Bath - Secondary | Shower | Metal trim (edge profile) - verify availability | Pending |  |  |  |  | W1-14 | V |  |  |  | V: confirm metal trim color + count
116 | Bath - Secondary | Shower | Threshold + bench top | Pending |  |  |  |  | W3-01 | M |  |  | Martin
117 | Bath - Secondary | Shower | Glass shower enclosure | Pending |  |  |  |  | W3-03 | A / V |  |  |  | In master line (both baths); Use existing inventory glass with black hardware (A provides); V must confirm width
122
118 | Bath - Secondary | Finishes | Pocket door - verify function + paint | Pending |  |  |  |  | W2-14 | H
123
119 | Bath - Secondary | Ventilation | Exhaust fan | Pending |  |  |  |  | W3-04 | V |  |  |  | Verify power supply; fan install in electrical contract
INTERIOR - FINISHES
120 | Interior - Finishes | Flooring | Tile - inspect grout 100% + clean 100% | Pending |  |  |  |  | W2-15
121 | Interior - Finishes | Flooring | LVP in bedrooms | Pending |  |  |  |  | W2-15
122 | Interior - Finishes | Flooring | Transitions - tile to LVP between rooms | Pending |  |  |  |  | W2-15 | A > V |  |  |  | A buys transitions; V installs
123 | Interior - Finishes | Trim | Baseboards - inspect 100%, paint + caulk | Pending |  |  |  |  | W2-14 | H
124 | Interior - Finishes | Trim | Door trim / casings - inspect 100%, paint + caulk | Pending |  |  |  |  | W2-14 | H
125 | Interior - Finishes | Trim | Crown molding - inspect 100%, paint + caulk | Pending |  |  |  |  | W2-14 | H
126 | Interior - Finishes | Whole house | Interior paint - walls, ceilings | Pending |  |  |  |  | W2-13 | H |  |  |  | H: paint finish inside + touch-ups
127 | Interior - Finishes | Whole house | Pre-final alignment punch - doors, door handles, drawers, closet doors | Pending |  |  |  |  | W2-20 |  |  |  |  | Alignment pass before final punch list; could be done W2
128 | Interior - Finishes | Whole house | Interior doors and hardware | Pending |  |  |  |  | W2-14 | H
129 | Interior - Finishes | Whole house | Window treatments - blinds | Pending |  |  |  |  | W3-08 | A + V |  |  |  | Request approval for blinds; V: confirm measurements; A: selection; approval needed
130 | Interior - Finishes | Closets | Master closet - IKEA | Pending |  |  |  |  | W2-18 | A + V |  |  |  | Purchase, assemble, install; A purchases ASAP (W1); transport V&A or A&H; V assembles + installs
131 | Interior - Finishes | Closets | Second closet - IKEA | Pending |  |  |  |  | W2-18 | A + V |  |  |  | Purchase, assemble, install; A purchases ASAP (W1); transport V&A or A&H; V assembles + installs
132
137
133 | Interior - Finishes | Garage | Garage shelf - install | Pending |  |  |  |  | W2-21 | A > V |  |  |  | A selects; V installs
134 | Interior - Finishes | Garage | Garage floor - repair + epoxy | Pending |  |  |  |  | W2-12 | A / V |  |  |  | A: ask expert why yellow stain; V: fix (labor)
139
135 | Interior - Finishes | Garage | Tool box / shelf from Delray storage | Pending |  |  |  |  | W3-13 | A + H |  |  |  | Transport + place; Organize storage (H & A); transport tool box to property (H & A)
CLOSEOUT
136 | Closeout | General | Final inspections - all trades | Pending |  |  |  |  | W3-14 |  |  |  |  | Roofing, windows/doors, electrical, plumbing, mechanical
137 | Closeout | General | Permit closeout / CO or CC | Pending |  |  |  |  | W3-15 |  |  |  |  | Incl. curing old AC permit violation
138 | Closeout | General | Punch list walkthrough | Pending |  |  |  |  | W3-17
139 | Closeout | General | Final window cleaning | Pending |  |  |  |  | W3-16 |  |  |  |  | Along with final pressure wash
140 | Closeout | General | Final deep clean | Pending |  |  |  |  | W3-18
141 | Closeout | General | Staging / photos (if listing) | Pending |  |  |  |  | W3-19
|  |  | TOTALS | [7 empty] | 55875 | 35475
EXTERIOR
15 | Exterior | Roof | Roof replacement | Complete |  |  |  |  | - |  | 30297 | 0 |  | Paid in full; final inspection pending
16 | Exterior | Roof | Gutters and downspouts | Complete |  |  |  |  | -
17 | Exterior | Roof | Fascia - 100% replacement + caulking | Complete |  |  |  |  | - |  |  |  |  | 100% caulked
18 | Exterior | Roof | Fascia + trim repaint | Pending |  |  |  |  | W2-05 | H |  |  |  | H: repaint + change color; A: confirm color choice
19 | Exterior | Roof | Soffit - replace vents, paint vents | Pending |  |  |  |  | W2-05 | H |  |  |  | H: install vents, paint vents, remove old mesh
20 | Exterior | Envelope | Stucco repair | Complete |  |  |  |  | -
21 | Exterior | Envelope | Stucco texture | Pending |  |  |  |  | W2-04 | S |  |  |  | A: find stucco sub
22 | Exterior | Envelope | Paint over textured stucco areas | Pending |  |  |  |  | W2-04 | H
23 | Exterior | Envelope | Exterior pressure washing - final closeout | Pending |  |  |  |  | W3-16 |  |  |  |  | Along with final window cleaning
24 | Exterior | Envelope | Exterior paint - full house | Complete |  |  |  |  | - |  |  |  |  | ARB approved
25 | Exterior | Windows/Doors | Impact windows + doors installation | Complete |  |  |  |  | - |  | 19825.36 | 0 |  | Paid in full ($300 credit applied); final inspection pending; remaining: decorative door panels + close-out trim
26 | Exterior | Windows/Doors | Patio (sliding) doors | Complete |  |  |  |  | - |  |  |  |  | Installed
27 | Exterior | Windows/Doors | Front entry door | Pending |  |  |  |  | W1-15 | A |  |  |  | Design pending; decorative door panels per window contract; A: call Reylos to schedule final install
28 | Exterior | Windows/Doors | Grid decoration - patio doors + kitchen door | Pending |  |  |  |  | W1-15 | A |  |  |  | Included in window contract remaining work; A: call Reylos to schedule final install
29 | Exterior | Windows/Doors | Exterior door handles | Pending |  |  |  |  | W3-12
30 | Exterior | Windows/Doors | Garage door (exterior) - hurricane rated | Pending |  |  |  |  | W2-11 | V+H / A | 7500 | 4500 |  | Swap with Jupiter unit; permit pending; $5,500-$7,500 installed range (HVHZ/wind-load compliance); incl. removal, reinforced tracks, wind-load hardware, motor reconnect, final inspection; A: rental van needed for transport
31 | Exterior | Windows/Doors | Interior garage door (house-to-garage) replacement | Pending |  |  |  |  | W3-12 | A > V |  |  |  | A purchases; V installs
32 | Exterior | Windows/Doors | Garage door opener | Pending |  |  |  |  | W2-11 |  |  |  |  | Install pending
33 | Exterior | Hardscape | Driveway pavers | In Progress |  |  |  |  | W1-19 | A / S | 10000 | 10000 |  | Order ready - arrange delivery + pallet placement; permit resubmission in process; labor $6,200-$7,000 + material ~$2,000 + sealant $2,000; 2-3 days on site; contact labor team; A: contact labor guy, contact supplier, arrange delivery; S does install; A: coordinate sub, arrange delivery, process permit, appointment for final quote, try to meet on site Monday
34 | Exterior | Hardscape | Paver brick sealing | Pending |  |  |  |  | W2-06 | S |  |  |  | ~$2,000 - included in driveway paver line above
35 | Exterior | Hardscape | Driveway asphalt overlay | Pending |  |  |  |  | W2-06 |  | 3000 | 3000 |  | Permit required (3-5 day review); HOA 2-3 days; 2-3 days labor; no concrete walkway included - confirm if alternative to pavers
36 | Exterior | Hardscape | Entry tile installation (walkway now part of pavers) | Pending |  |  |  |  | W2-07 | A / S | 2000 | 1500 | Victor | Material ~$600; repair 2+ concrete sections (Victor, 2 days @ $300/day); cut root beneath slab; level surface; tile installer 2 days $600-$800; open sides + vertical tile if metal trim edge desired; generates demo waste; direct supervision required; REVISED SCOPE: walkway stays concrete - covered under pavers; S tiles ENTRY at same time as shower tile; A: tile selection; tile MUST happen BEFORE pavers
37 | Exterior | Hardscape | Patio - drainage + repairs | Pending |  |  |  |  | W2-08 | V / H / S |  |  |  | Cost TBD - inspect drain system, repair as needed, install side drain cover, replace metal screen piece near drain, protect adjacent tile; finish drain pipes; glue broken tile; V: fix drain; H: make hole + cover with soil; S (tile): fix broken piece
38 | Exterior | Landscape | Front yard design | Pending |  |  |  |  | W1-16 | A |  | 2500 |  | Design decision pending; A: obtain labor quote + materials quote; provide Jaime with design proposal
39 | Exterior | Landscape | Backyard design | Pending |  |  |  |  | W1-16 | A |  |  |  | TBD - deck proposal under review; permit may be required depending on deck size; A: obtain labor quote + materials quote; provide Jaime with design proposal
40 | Exterior | Landscape | Side yard design | Pending |  |  |  |  | W1-16 | A |  |  |  | TBD; A: obtain labor quote + materials quote; provide Jaime with design proposal
41 | Exterior | Landscape | Grass installation (front only) | Pending |  |  |  |  | W3-11 | S |  |  |  | TBD; With landscape build-out; timing W1-W3 depending on design decision + sub availability
42 | Exterior | Landscape | Tree trimming / removal | Pending |  |  |  |  | W2-10 | S |  |  |  | Possible side palm removal; landscape build-out
43 | Exterior | Landscape | Sprinkler system | Pending |  |  |  |  | W2-09 | S |  | 500 |  | Check all heads; verify timer operation all 3 zones; replace broken pipes as needed; S: repair, verify timer, build pipelines as needed
44 | Exterior | Landscape | Sprinkler pump box cover | Pending |  |  |  |  | W2-09 | A |  |  |  | A: buy or inquire
45 | Exterior | Landscape | Fence | Not Needed |  |  |  |  | -
46 | Exterior | Pool | Pool (resurfacing, equipment, deck) | Not Needed |  |  |  |  | - |  |  |  |  | No pool
47 | Exterior | Screen Enclosure | Rescreen + structure pressure wash and paint | Complete |  |  |  |  | -
48 | Exterior | Screen Enclosure | Screen door - alignment + lock functionality | Pending |  |  |  |  | W3-12 |  |  |  |  | Confirm alignment and lock work
49 | Exterior | Finishes | Exterior light fixtures | Pending |  |  |  |  | W2-02 |  |  |  |  | Install flood lights and sconces (floodlight in electrical contract)
50 | Exterior | Finishes | House numbers and mailbox | Pending |  |  |  |  | W3-12 |  |  |  |  | Verify condition
51 | Exterior | Finishes | Hose bibs | Complete |  |  |  |  | - |  |  |  |  | Repaired / replaced as needed
Note on I30: Proposed: interior demolition complete; dumpster/waste stays open through primer.
Note on O34: Status/notes look carried over from the previous property template; the 21-Sep session reports Jupiter fully stripped with no MEP work done - verify status, cost and balance.
Note on O47: Status/notes look carried over from the previous property template; the 21-Sep session reports Jupiter fully stripped with no MEP work done - verify status, cost and balance.
Note on O49: Status/notes look carried over from the previous property template; the 21-Sep session reports Jupiter fully stripped with no MEP work done - verify status, cost and balance.
Note on O52: Status/notes look carried over from the previous property template; the 21-Sep session reports Jupiter fully stripped with no MEP work done - verify status, cost and balance.
Note on O59: Status/notes look carried over from the previous property template; the 21-Sep session reports Jupiter fully stripped with no MEP work done - verify status, cost and balance.
Note on O67: Status/notes look carried over from the previous property template; the 21-Sep session reports Jupiter fully stripped with no MEP work done - verify status, cost and balance.
Note on O68: Status/notes look carried over from the previous property template; the 21-Sep session reports Jupiter fully stripped with no MEP work done - verify status, cost and balance.
Note on O74: Status/notes look carried over from the previous property template; the 21-Sep session reports Jupiter fully stripped with no MEP work done - verify status, cost and balance.
Note on O77: Status/notes look carried over from the previous property template; the 21-Sep session reports Jupiter fully stripped with no MEP work done - verify status, cost and balance.
Note on O78: Status/notes look carried over from the previous property template; the 21-Sep session reports Jupiter fully stripped with no MEP work done - verify status, cost and balance.
Note on O81: Status/notes look carried over from the previous property template; the 21-Sep session reports Jupiter fully stripped with no MEP work done - verify status, cost and balance.
Note on O84: Marked Not Needed here, but the framing row (Demo/Structure) lists a kitchen island and the session describes an open-concept kitchen - confirm with the approved kitchen layout.

## Schedule Logic
SCHEDULE LOGIC - PRE-CONSTRUCTION, DEMO/STRUCTURE, ELECTRICAL, PLUMBING, HVAC, KITCHEN (proposed baseline)
Working days Mon-Fri excluding holidays in column M. Edit only the yellow cells (baseline) and blue cells (lag, duration, effort); Start/End recalculate and feed Scope Checklist columns F-H.
Baseline start |  | 2026-10-05 | Set by Andrés/Carlos on 24-Sep-2026 (leaves week of 28-Sep to close ARV / max-budget analysis)
Scope row | # | Scope Item | Predecessor (logic) | Lag (wd) | Duration (wd) | Start | End | Effort (hrs) | Owner | Basis / Source | Holidays
PRE-CONSTRUCTION | [10 empty] | 2026-11-11 | Veterans Day (city offices closed)
8 | 2 | Determine specification sheets (Render) | Baseline start | 0 | 10 | 2026-10-05 | 2026-10-16 | 40 | A | [10:25]-[11:15] one spec sheet (render) per room; must be validated by Jaime. Gate: max renovation budget from comps/ARV [43:15] | 2026-11-26 | Thanksgiving
16 | 9 | Obtain access to Online Portal | Baseline start | 0 | 2 | 2026-10-05 | 2026-10-06 | 2 | A | [31:37] MGO portal - select jurisdiction (Town of Jupiter); confirm county Palm Beach vs Martin [30:34] | 2026-11-27 | Day after Thanksgiving
7 | 1 | Architecture & Engineering design and proposal | Starts 5 wd after spec sheets start (as-built first) | 5 | 15 | 2026-10-12 | 2026-10-30 | 60 | A / Sub | [32:44]-[33:38] as-built + proposed plans incl. M/E/P; drafted in-house [38:25] - recommend delegating | 2026-12-24 | Christmas Eve
9 | 3 | Architecture & Engineering Approval | After A&E design | 0 | 5 | 2026-11-02 | 2026-11-06 | 6 | A | [39:37]-[39:48] engineer signs/seals before city submittal | 2026-12-25 | Christmas
10 | - | Select provides and assign budget | After spec sheets | 0 | 15 | 2026-10-19 | 2026-11-06 | 24 | A | [28:00]-[28:29] kitchen cabinets 3-4 wk fabrication = long-lead item; everything else available immediately | 2027-01-01 | New Year's Day
12 | 5 | HOA / ARB approval - Garage Door | After spec sheets | 0 | 15 | 2026-10-19 | 2026-11-06 | 3 | A | Assumption: ARB review ~3 weeks; confirm HOA meeting calendar
13 | 6 | HOA / ARB approval - exterior paint | After spec sheets | 0 | 15 | 2026-10-19 | 2026-11-06 | 3 | A | Assumption: submitted together with garage door package
14 | 7 | HOA / ARB approval - driveway | After spec sheets | 0 | 15 | 2026-10-19 | 2026-11-06 | 3 | A | [26:43] driveway quoted $15-18k; ARB approval before permit
15 | 8 | HOA / ARB approval - Landscaping | After spec sheets | 0 | 15 | 2026-10-19 | 2026-11-06 | 3 | A | [12:39] new entrance, fence + lighting concept
17 | 10 | Certificate of insurance per trade per jurisdiction | 5 wd after provider selection starts | 5 | 10 | 2026-10-26 | 2026-11-06 | 6 | A | Needed per trade for sub-permits (County, City, HOA)
18 | 11 | Workers compensation per trade | 5 wd after provider selection starts | 5 | 10 | 2026-10-26 | 2026-11-06 | 4 | A | Collected with COI; ongoing document
19 | 12 | DBPR license per trade | 5 wd after provider selection starts | 5 | 10 | 2026-10-26 | 2026-11-06 | 3 | A | License check per trade before permit application
21 | 14 | Permits package submittal | After sealed plans + portal + COI | 0 | 3 | 2026-11-09 | 2026-11-12 | 12 | A | [33:22] city requires independent application per trade under the master project
20 | 13 | Notice of Commencement (NOC) | After package submittal | 0 | 3 | 2026-11-13 | 2026-11-17 | 4 | A | Record before first inspection (FL 713.13); confirm county
22 | 15 | GC master permit - Residential alterations and additions | After package submittal | 0 | 20 | 2026-11-13 | 2026-12-14 | 8 | A | [33:38]-[34:51] master ('papa') permit covers all sub-permits; assumes 1 round of review comments
23 | 16 | Mechanical permit | 5 wd after master permit review starts | 5 | 15 | 2026-11-20 | 2026-12-14 | 4 | A | [33:19] Mechanical sub-permit; cures AC items
24 | 17 | Electrical permit | 5 wd after master permit review starts | 5 | 15 | 2026-11-20 | 2026-12-14 | 4 | A | [33:16] Electrical sub-permit
25 | 18 | Plumbing permit | 5 wd after master permit review starts | 5 | 15 | 2026-11-20 | 2026-12-14 | 4 | A | [34:24] Plumbing sub-permit - critical path for baths
26 | 19 | Fence permit | After package + ARB landscaping | 0 | 10 | 2026-11-13 | 2026-11-30 | 3 | A + V | [08:44] existing fence to be removed/replaced
27 | 20 | Driveway permit | After package + ARB driveway | 0 | 10 | 2026-11-13 | 2026-11-30 | 3 | A + V | [26:24] driveway; exterior - not on interior critical path
28 | 21 | Gazebo permit | After package + ARB landscaping | 0 | 10 | 2026-11-13 | 2026-11-30 | 3 | A | [13:15] BBQ / outdoor area concept
29 | 22 | Garage-door permit | After package + ARB garage door | 0 | 10 | 2026-11-13 | 2026-11-30 | 3 | A | Garage door replacement permit
30 | 23 | Demolition & Waste Management | Baseline start -> end of primer (N5) | 0 | 76 | 2026-10-05 | 2027-01-26 | 10 | A | Dumpster kept through demo/structure phase
31 | 24 | Utilities | Baseline start -> closeout | 0 | - | 2026-10-05 | Ongoing | 2 | A | Ongoing - autopay
INTERIOR - DEMO/STRUCTURE
35 | N1 | Site protection + inventory (windows, railings, outlets, switches, smoke detectors) | Baseline start | 0 | 2 | 2026-10-05 | 2026-10-06 | 12 | A + V | [16:10]-[17:08] protect windows/railings, inventory + cover outlets/switches/smoke detectors; acta: before any new intervention
36 | N2 | Structural engineering review - removed interior walls / truss bearing | Baseline start (feeds A&E design) | 0 | 8 | 2026-10-05 | 2026-10-14 | 8 | A / Sub | [14:41]-[15:36] load-bearing check of removed walls; trusses bear on perimeter - needs sealed letter
37 | 56 | Popcorn ceiling removal - flat finish & skin coat | After site protection | 0 | 8 | 2026-10-07 | 2026-10-16 | 64 | Sub | No permit needed; asbestos test first (industry practice); final skim folded into drywall final
38 | 53 | Framing repairs / new partitions | After GC master permit issued + engineer letter | 0 | 5 | 2026-12-15 | 2026-12-21 | 60 | V | [14:41] engineer approval; permitted work cannot start before issuance
39 | N3 | Slab trench patch after underground plumbing (baths/kitchen) + slab inspection | After underground DWV inspection PASS (N8) | 0 | 3 | 2026-12-21 | 2026-12-23 | 16 | V | [52:36]-[53:16] underground inspection, then slab + plumbing inspections simultaneously
40 | 57 | Concrete slab repair + tile infill under AC unit | After mechanical permit | 0 | 2 | 2026-12-15 | 2026-12-16 | 12 | V / Sub | Existing scope note; same crew as N3
41 | N4 | Framing + MEP rough-in inspections (pre-cover milestone) | After framing, slabs, panel, electrical rough-in (N7), plumbing top-out (N9) + duct modifications (N10) | 0 | 5 | 2026-12-31 | 2027-01-07 | 8 | A | [35:22]-[36:34] each step waits for next-day inspector; buffer for 1 re-inspection
42 | - | Drywall repair / install & finish. 2nd phase | After inspections PASS | 0 | 5 | 2027-01-08 | 2027-01-14 | 80 | V | Hang + tape new partitions; corner bead
43 | - | Drywall repair / install & finish. Final phase | After drywall 2nd phase | 0 | 5 | 2027-01-15 | 2027-01-21 | 60 | V | Finish, sand, ceiling final skim
44 | N5 | Surface prep - primer on walls + ceilings | After drywall final | 0 | 3 | 2027-01-22 | 2027-01-26 | 40 | H | [18:17]-[19:44] primer coat on walls + ceilings before wet trades
LINK TO FINISH TRADES (PROVISIONAL)
- | - | Finish trades ready for MEP trim (milestone) | PROVISIONAL: primer end + 20 wd - re-link to Kitchen/Bath rows once scheduled | 20 | 1 | 2027-02-24 | 2027-02-24 | - | A | Sheet data: cabinets install 1-2 d, bath tile ~10 d, countertops field measure + 5-d fabrication + install = ~20 wd before MEP trim
INTERIOR - ELECTRICAL
48 | N6 | Make-safe exposed wiring from demolition (cap, label, temp lighting) | Baseline start (safety, before trades return) | 0 | 1 | 2026-10-05 | 2026-10-05 | 6 | Sub | [14:34]-[14:41] exposed cables after wall removal
49 | 60 | Electrical panel change out | After electrical permit | 0 | 2 | 2026-12-15 | 2026-12-16 | 12 | A + V | Existing scope; coordinate utility disconnect/reconnect; inspected with rough-in (N4)
50 | N7 | Electrical rough-in - relocated boxes, new kitchen/bath circuits | After electrical permit + framing | 0 | 5 | 2026-12-22 | 2026-12-30 | 60 | Sub | [12:07]-[12:38] open kitchen, removed partitions; [33:16] electrical sub-permit
51 | 61 | Outlets, switches, GFCI/AFCI | Trim window (PROVISIONAL anchor) | 0 | 3 | 2027-02-25 | 2027-03-01 | 24 | Sub | Existing scope: incl. dedicated fridge + oven outlets
52 | 62 | Recessed lighting (LED) | With outlets (same electrician visit) | 0 | 2 | 2027-02-25 | 2027-02-26 | 12 | Sub | Cans set at rough-in (N7); trims after paint
53 | 63 | Ceiling fans | 1 wd after outlets start | 1 | 2 | 2027-02-26 | 2027-03-01 | 12 | Sub | Existing scope: patio, master, bed 2, bed 3, living
54 | 64 | Dining fixture (kitchen chandelier) | 2 wd after outlets start | 2 | 1 | 2027-03-01 | 2027-03-01 | 3 | Sub | Existing scope: reposition box at rough-in
55 | 65 | LED mirrors - install | After outlets (vanities + tile in place) | 0 | 1 | 2027-03-02 | 2027-03-02 | 4 | V | Existing scope
56 | 66 | Smoke / CO detectors - replace all | After outlets | 0 | 1 | 2027-03-02 | 2027-03-02 | 4 | V > A | [16:49]-[16:55] detectors covered during works; replace at trim
57 | 67 | Doorbell / smart doorbell | After outlets | 0 | 1 | 2027-03-02 | 2027-03-02 | 2 | Sub | Existing scope
47 | 59 | Electrical contract - overall | Umbrella: make-safe start -> last electrical item | 0 | 101 | 2026-10-05 | 2027-03-02 | - | Sub | Contract envelope; hours carried by the detail rows
INTERIOR - PLUMBING
60 | N8 | Underground DWV rough-in (baths/kitchen) incl. P-traps + underground inspection PASS | After plumbing permit (3 wd work + 1 wd inspection) | 0 | 4 | 2026-12-15 | 2026-12-18 | 32 | V | [50:25]-[52:36] missing trap -> sewer gas -> shower rebuilt; [52:23] underground inspection before slab
61 | N9 | Water supply rough-in / top-out (shower valves, toilets, kitchen, fridge line) + pressure test | After slab patch (N3) | 0 | 3 | 2026-12-28 | 2026-12-30 | 24 | V | [53:00]-[53:16] inspector checks penetrations + blocking
62 | 71 | Plumbing inventory check - supply lines, drainage, P-traps | After top-out (quantities known) | 0 | 2 | 2026-12-31 | 2027-01-04 | 6 | V | Buy P-traps/supply lines early; only long-lead item is kitchen cabinets [28:29]
63 | 69 | Final plumbing completion labor | Trim window (PROVISIONAL anchor) | 0 | 3 | 2027-02-25 | 2027-03-01 | 24 | V | Existing scope: ~3 days at Victor's daily rate
64 | 72 | Angle stops and supply lines throughout | With final plumbing labor | 0 | 2 | 2027-02-25 | 2027-02-26 | 8 | V | Existing scope
INTERIOR - HVAC
69 | N10 | Duct modifications - removed partitions, kitchen hood + bath exhaust ducting | After mechanical permit + framing | 0 | 3 | 2026-12-22 | 2026-12-28 | 24 | Sub | [33:19] mechanical sub-permit; [12:07] removed partitions; must be in before N4 inspection
70 | 77 | Ductwork inspection / repair / clean | After primer (dusty work finished) | 0 | 2 | 2027-01-27 | 2027-01-28 | 16 | Sub | Industry practice: clean ducts after sanding, not before
71 | 75 | HVAC coil cleaning | After primer (with duct cleaning visit) | 0 | 1 | 2027-01-27 | 2027-01-27 | 4 | Sub | Existing scope: part of maintenance line
72 | 76 | HVAC coolant refill service | Same visit as coil cleaning | 0 | 1 | 2027-01-27 | 2027-01-27 | 3 | Sub | Existing scope: part of maintenance line
73 | 78 | AC diffusers | Trim window (PROVISIONAL anchor) | 0 | 1 | 2027-02-25 | 2027-02-25 | 4 | A | Existing scope: purchase early, install after final paint
74 | 79 | Thermostat | Trim window (PROVISIONAL anchor) | 0 | 1 | 2027-02-25 | 2027-02-25 | 2 | V | Existing scope
68 | 74 | HVAC maintenance + concrete slab repair | Umbrella: AC slab repair start -> last maintenance item | 0 | 30 | 2026-12-15 | 2027-01-28 | - | A / Sub | Contract envelope ($2,100); hours carried by the detail rows
KITCHEN
76 | N11 | Cabinet order - field-verify dimensions, PO + fabrication (3-4 wk) | After framing (dimensions fixed) + provider selection | 0 | 20 | 2026-12-22 | 2027-01-21 | 6 | A | [28:00]-[29:44] fabrication 3-4 wk; cash constraint -> order just in time; [13:21] layout needs Jaime approval
77 | 80 | Kitchen cabinets + bathroom vanities (combined contract) | After primer + cabinet delivery | 0 | 2 | 2027-01-27 | 2027-01-28 | 16 | A + V | Sheet: install by manufacturer 1-2 days max; A + V verify quality on site. Vanities follow the bath sequence
78 | 81 | Stone countertops + backsplash (kitchen + baths) | After cabinets set (field template) | 0 | 8 | 2027-01-29 | 2027-02-09 | 12 | A / M | Sheet: template after cabinets set -> ~5 business days fabrication -> install 1-2 days; same slab for vanities/thresholds saves $
79 | 82 | Kitchen sink - purchase | 5 wd into cabinet fabrication (must be on site for template) | 5 | 5 | 2026-12-31 | 2027-01-07 | 3 | A | Undermount sink needed for countertop cut-out
80 | 83 | Kitchen faucet | 5 wd into cabinet fabrication | 5 | 5 | 2026-12-31 | 2027-01-07 | 2 | V > A | Verify if already purchased; faucet hole count for template
81 | 84 | Appliance package - purchase, transport, install | 5 wd into cabinet fabrication (specs frozen before order) | 5 | 10 | 2026-12-31 | 2027-01-14 | 16 | A | Sheet: appliance package; fridge + cooktop + hood dimensions drive cabinet order and countertop cut-outs
82 | N12 | Appliance install + hook-ups (oven, cooktop, DW, disposal, hood, fridge line) | After countertops + electrical/plumbing trim | 0 | 2 | 2027-03-02 | 2027-03-03 | 12 | V | Dedicated circuits from rough-in (N7); DW/disposal need final plumbing
83 | 86 | Under-cabinet lighting | With electrical trim (after countertops/backsplash) | 0 | 1 | 2027-02-25 | 2027-02-25 | 4 | A | Existing scope: transformer + LED strip / puck lights
Milestones
|  | Permits issued (GC master + M/E/P) |  |  |  |  | 2026-12-14
|  | Framing + MEP rough-in inspections passed |  |  |  |  | 2027-01-07
|  | Demo/Structure phase complete (primer done) |  |  |  |  | 2027-01-26
|  | Underground plumbing inspection passed |  |  |  |  | 2026-12-18
|  | Finish trades ready for MEP trim (PROVISIONAL) |  |  |  |  | 2027-02-24
|  | Electrical complete (trim) |  |  |  |  | 2027-03-02
|  | Plumbing complete (trim) |  |  |  |  | 2027-03-01
|  | HVAC complete (diffusers + thermostat) |  |  |  |  | 2027-02-25
|  | Kitchen countertops installed |  |  |  |  | 2027-02-09
|  | Kitchen complete (appliances installed) |  |  |  |  | 2027-03-03
|  | Total effort - Pre-Construction (hrs) | [5 empty] | 217
|  | Total effort - Demo/Structure (hrs) | [5 empty] | 360
|  | Total effort - Electrical (hrs) | [5 empty] | 139
|  | Total effort - Plumbing (hrs) | [5 empty] | 94
|  | Total effort - HVAC (hrs) | [5 empty] | 53
|  | Total effort - Kitchen (hrs) | [5 empty] | 71
Formulas:
Start = WORKDAY(G7,[Lag (wd)],M6:M11)
Start = WORKDAY([End, row above],1+[Lag (wd)],M6:M11)
End = WORKDAY([Start],[Duration (wd)]-1,M6:M11)
End = MAX(H46,H47,H48,H49,H50,H51,H52,H53,[End, row above])
Duration (wd) = NETWORKDAYS([Start],[End],M6:M11)

## 3-Week Plan
3-WEEK EXECUTION PLAN - A = Andres ¦ V = Victor ¦ H = Hans ¦ S = Sub ¦ M = Martin (stone) ¦ G = Gino (glass)
Codes match 'Exec Order' column on Scope Checklist
WEEK 1 - UNBLOCK: permits, inspections, decisions, purchases, wet-area rough
Code | Owner | Task
W1-01 | A | Record NOC with Broward County (required before first inspection)
W1-02 | A | Push issuance: GC master permit + plumbing sub-permit (bathrooms) - CRITICAL PATH for shower pan inspection
W1-03 | A | Driveway permit resubmission
W1-04 | A | Windows/doors/garage door permit - push forward; schedule inspection
W1-05 | A + V | Electrical permit: A paperwork; V provides labels for panel, amperage, service
W1-06 | A + V | Mechanical permit (cure AC violation): A paperwork + qualifier ~$800 fee; V photographs equipment label (model + tonnage)
W1-07 | - | Roofing - COMPLETE, no further action
W1-08 | V | Master bath drywall: finish, compound, sand, paint; detach vanity + back wall; confirm faucet height + countertop height for sink type selection
W1-09 | A / V / Sub | HVAC: A hires service (coil clean, coolant, filter, duct check); V demos closet tile + installs new tile at unit
W1-10 | A + V | Panel installed: V adds labels to cover + identifies amperage/service; A schedules + passes inspection
W1-11 | A + V | Mon Jul 6, 11 AM - both at Noel cabinet quality appointment -> release manufacturer install (1-2 days); verify vanities same visit
W1-12 | A / V / M | Martin meeting Sat Jul 4 - V attends; M provides quote; A selects stone (kitchen vs vanities vs thresholds - same slab saves $), A purchases + makes down payment
W1-13 | A / V | A purchases: kitchen sink, bath sinks, shower drains (both baths - select + buy); V verifies faucet purchased, if not A buys
W1-14 | A / V | A PURCHASE SESSION (Amazon / online / retail): appliances (marketplace), under-cabinet LED, diffusers, LED mirrors, bath hardware, outlets + switches. V: count smoke detectors, pack + return thermostat via UPS, confirm metal trim color + count, provide fridge depth (width = 36 in)
W1-15 | A | Call Reylos to schedule final install; front door design + grid decoration (needed before window final inspection)
W1-16 | A | Landscape: obtain labor quote + materials quote; provide Jaime with design proposal (front, backyard deck - permit?, side)
W1-17 | V | Shower prep: confirm metal frame distance + shower door frame support, both baths; labor if needed
W1-18 | V | Shower sequence, both baths - after permit issuance + plumbing/framing/slab inspections: (1) frame, (2) pan liner + PASS inspection, (3) Durock, (4) waterproofing. Gates all tile
W1-19 | A | Pavers: contact labor guy, contact supplier, arrange delivery + pallet placement
W1-20 | V | Toilets - both baths: install w/ new wax rings; new flange if necessary; verify supply line + drainage positioning
W1-21 | Sub | Bathtub electrical connection - roughed + READY FOR INSPECTION (in electrical contract); tub sets W2 after inspections pass
WEEK 2 - PRODUCTION: tile marathon, electrical finish, exterior, paint
Code | Owner | Task
W2-01 | S | Sub STARTS bathroom tile - both baths (~10 days, runs into W3). Only after W1-18 + inspections. Also open exhaust fan holes so fans are install-ready
W2-02 | Sub / V | Electrical finish: outlets/switches/GFCI (incl. dedicated fridge + oven outlets), ceiling fans, chandelier box + install, floodlight, kitchen LED, patio recessed fix, doorbell. V: LED niches ASAP - confirm inventory or order supply (before tile)
W2-03 | V | Victor plumbing (~3 days): angle stops, supply lines; inventory check - supply lines, drainage, P-traps for kitchen + bath faucets, toilets (list + purchase gaps)
W2-04 | S / H | S: stucco texture (A finds stucco sub); H: paint over textured areas
W2-05 | H / A | H: fascia + trim repaint (change color), soffit vents install + paint, remove old mesh; A: confirm color choice
W2-06 | A / S | Pavers: S installs + seals; A coordinates sub, arranges delivery, processes permit, sets final quote appointment, tries to meet on site Monday
W2-07 | A / S | ENTRY TILE (walkway stays concrete - part of pavers): A selects tile; S installs at same time as shower tile; MUST happen before pavers
W2-08 | V / H / S | Patio drainage: V fixes drain; H makes hole + covers with soil; S (tile) fixes broken piece
W2-09 | S / A | S: sprinkler repair, timer verify, build pipelines as needed; A: buy or inquire pump box cover
W2-10 | S | Tree trimming, possible side palm removal, landscape build-out
W2-11 | V+H / A | Garage door swap with Jupiter unit + opener; A: rent van for transport
W2-12 | A / V | Garage floor: A asks expert why yellow stain; V fixes (labor); epoxy
W2-13 | H | Interior paint: finish inside + touch-ups
W2-14 | H | Inspect + finish paint ALL trim: baseboards, casings, crown, interior doors + hardware, pocket doors (function + paint), master finish trim
W2-15 | A > V | Floor transitions: A buys, V installs; LVP bedrooms; grout inspect + clean 100%
W2-16 | A / M | Martin field measure after cabinets set -> 5-day fabrication clock
W2-17 | V | Set tub after inspections pass (electrical connected W1-21)
W2-18 | A + V | IKEA closets: A purchases W1 ASAP; transport V&A or A&H; V assembles + installs (master + second)
W2-19 | V | Corner bead + window sills - finish + paint AFTER window inspection
W2-20 | TBD | Pre-final alignment punch: doors, door handles, drawers, closet doors
W2-21 | A > V | Laundry shelf + garage shelf: A selects; V installs
WEEK 3 - FINISH + CLOSE: stone, glass, fixtures, inspections
Code | Owner | Task
W3-01 | M | Countertop + backsplash install (~5 days after quote; subject to stone purchase + delivery availability); thresholds + bench tops
W3-02 | V | Install faucets + sinks - both baths + kitchen (verify vanity heights). (Toilets moved to W1-20)
W3-03 | G / A / V | Master: Gino quotes + installs glass. Secondary: existing inventory glass w/ black hardware (A provides); V confirms width
W3-04 | V | Install LED mirrors + exhaust fans (master duct coupling; secondary power supply); bath hardware (purchased W1)
W3-06 | V | Appliances: final installs/connections as acquired (transport + install runs W1-W2)
W3-08 | A + V | Blinds: V confirms measurements; A selects; approval needed; install
W3-11 | S | Grass (front) + landscape build-out - timing W1-W3 per design decision + availability
W3-12 | A > V | Small items: house numbers/mailbox, screen door alignment/lock, exterior handles; interior garage door - A purchases, V installs
W3-13 | A + H | Organize storage; transport tool box to property
W3-14 | A | FINAL INSPECTIONS: windows/doors, electrical, plumbing, mechanical (AC violation cured)
W3-15 | A | Permit closeout - all permits, CO/CC
W3-16 | TBD | Final pressure wash + window cleaning
W3-17 | A | Punch list walkthrough
W3-18 | TBD | Final deep clean
W3-19 | TBD | Staging + photos
Moved | - | Earlier: toilets -> W1-20 (V); tub set -> W2-17 (V); closets -> W2-18 (A+V); trim/doors -> W2-14 (H); corner bead -> W2-19 (V); LED mirror/hardware/outlet purchases -> W1-14 (A)
Critical path: permits -> W1-18 shower sequence -> S tile (10 days) -> Gino measure/fab -> glass install. Stone chain: Jul 4 Martin quote -> Jul 6 cabinets -> field measure -> 5-day fab -> W3-01 install. Entry tile before pavers; pavers permit-dependent.

## Cost Summary
PROJECT STATUS & COST SUMMARY
101 W Bayridge Dr, Weston, FL 33326 - per uploaded cost summary
Category | Item | Total Cost | Credits | Balance Due | Permit / Inspection Status | Remaining Work
Roofing | Roof Replacement | 30297 |  | 0 | Final Inspection Pending | None
Windows | Window Installation | 19825.36 | 300 | 0 | Final Inspection Pending | Decorative door panels + close-out trim
Electrical | Electrical Work | 14000 | 0 | 7000 | Final Inspection Pending | Light fixtures + fans, all outlets + switches, kitchen chandelier, exterior floodlight, kitchen LED, bath exhaust fans, bathtub electrical, LED mirrors
Plumbing | Final Plumbing (labor factored separately) |  | 0 | 1500 | Final Inspection Pending | ~3 days labor at Victor's daily rate
Tile Work | Bathroom Tile Installation (labor) |  | 0 | 3500 | N/A | Complete bathroom tile install, both baths; ~10 days
Shower Glass | Shower Glass Fabrication + Install | 3000 | 0 | 3000 | N/A | Fabrication ~4 days; install 1-2 days
Cabinetry | Kitchen Cabinets + Bathroom Vanities | 21750 | 0 | 4875 | N/A | Install by manufacturer, 1-2 days max
Countertops | Stone Countertops + Backsplash | 5925 | 0 | 4500 | N/A | $50-$75/sq ft; kitchen ~35sf counter + ~25sf backsplash; bath2 ~8sf, master ~11sf; fab ~5 days; cabinets must be installed before field measure
Appliances | Appliance Purchase Package | 9100 | 0 | 9100 | N/A | Samsung oven+micro $3,700; cooktop $650; DW $500; hood $500; disposal $250; wine cooler $450; fridge $1,800; W+D $1,250
Landscaping | Sprinkler System |  | 0 | 500 | N/A | Check heads; verify timer, all 3 zones; replace broken pipes
Landscaping | Front Yard Design |  | 0 | 2500 | N/A | TBD
Landscaping | Backyard Design |  | 0 |  | Pending Review | Deck proposal under consideration; permit may be required by deck size
Landscaping | Side Yard Design |  | 0 |  | N/A | TBD
Landscaping | Grass Installation (Front Only) |  | 0 |  | N/A | TBD
Driveway + Walkway | Pavers | 10000 | 0 | 10000 | Permit Required | Labor $6,200-$7,000; material ~$2,000; sealant $2,000; permit 3-5 day review; HOA 2-3 days; 2-3 days on site
Driveway | Asphalt Overlay | 3000 | 0 | 3000 | Permit Required | Permit 3-5 day review; HOA 2-3 days; 2-3 days labor; no concrete walkway
Walkway | Tile Installation Proposal | 2000 | 0 | 1500 | TBD | Material ~$600; Victor concrete repair 2 days @$300/day; root cut; leveling; tile installer 2 days $600-$800
Drainage | Patio Drain Inspection + Repair |  | 0 |  | N/A | Inspect + repair drain; side drain cover; replace metal screen piece; protect adjacent tile
HVAC | HVAC Maintenance + Concrete Slab Repair | 2100 | 0 | 2000 | Permit + Inspection Required | Maintenance; slab under equipment needs repair; cost depends in-house vs full replace
Garage Door | Hurricane-Rated Garage Door Replacement | 7500 | 0 | 4500 | Permit Required | HVHZ/wind-load compliant 16x7 insulated steel; incl. permit, removal, reinforced tracks, wind-load hardware, motor reconnect, final inspection
| TOTAL BALANCE DUE (pending items to 100% completion) |  |  | 57475
Note: source PDF states $52,975 pending total; line items above sum higher - reconcile (likely asphalt overlay/walkway as alternates or garage door exclusion)
PROJECT SPEND SUMMARY
| 2025 | 2026 | Total
Checking account (labor + materials + utilities + HOA + services) | 107414.33 | 24481.58 | 131895.91
Credit card (labor + materials + utilities + HOA + services) | 22180.93 | 12294.9 | 34475.83
SUBTOTAL | 129595.26 | 36776.48 | 166371.74
PROJECT TOTAL TO DATE |  |  | 166371.74

## Summary
RENOVATION SUMMARY BY CATEGORY
101 W Bayridge Dr, Weston, FL 33326
Category | Items | Pending | In Progress | Complete | Not Needed | Total Cost | Balance Due
Pre-Construction | 25 | 22 | 2 | 1 | 0 | 0 | 0
Exterior | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interior - Demo/Structure | 13 | 10 | 0 | 2 | 1 | 0 | 0
Interior - Electrical | 11 | 8 | 3 | 0 | 0 | 14000 | 7000
Interior - Plumbing | 7 | 5 | 0 | 1 | 1 | 0 | 1500
Interior - HVAC | 8 | 7 | 0 | 0 | 1 | 2100 | 2000
Kitchen | 9 | 7 | 1 | 0 | 1 | 36775 | 18475
Bath - Master | 19 | 19 | 0 | 0 | 0 | 3000 | 6500
Bath - Secondary | 14 | 14 | 0 | 0 | 0 | 0 | 0
Interior - Finishes | 15 | 15 | 0 | 0 | 0 | 0 | 0
Closeout | 6 | 6 | 0 | 0 | 0 | 0 | 0
TOTAL | 127 | 113 | 6 | 4 | 4 | 55875 | 35475